# SOs Children’s Village/ in somaliland

Request for Re-advertisement proposal and 
ToR for Consultancy to Conduct External  Evaluation SOS Emergecny Respose Project.

Somaliland

November 2021

Table of Contents

SOs Children’s Village in somaliland	1

1	Context and rationale	3

1.1	About SOS Children’s Villages	3

1.2	Description of project locations and context	3

1.3	Rationale and overall objective of the request for proposal of the evaluation of Somali Joint Response Project.	4

2	Instruction to bidders	4

2.1	Process of Submission of Bids	5

2.2	Documents to submit	5

2.3	Deadline for submission	5

2.4	Modification and withdrawal of bids	5

2.5	Signing of the contract	5

2.6	Rights of SOS Children’s Villages	6

2.7	Evaluation of proposals	6

3	Terms of Reference	6

3.1	Objectives of the evaluation	6

3.1.1	Overall objective	6

3.1.2	Specific objectives	6

3.1.3	Scope	9

3.2	Work plan and expected deliverables	10

3.3	Report criteria	10

3.4	Qualification of the researcher / research team	11

3.5	Logistical arrangements	11

3.6	Timetable	11

3.7	Duration of the contract and terms of payment	12

3.8	Notice of delay	12

3.9	Copyright and other proprietary rights	12

3.10	Termination	13

4	Annex	14

4.1	SOS Children’s Villages child protection policy and code of conduct	14

4.2	Bid submission / identification form	15

4.3	Previous experience form	16

4.4	Price schedule form	17

4.5	Technical proposal (guideline)	18

# Context and rationale

## About SOS Children’s Villages

SOS Children’s Villages is a global federation of 136 national SOS Children’s Villages associations, working in more than 2000 programme locations worldwide. We work together with a single vision: every child belongs to a family and grows with love, respect and security.

SOS Children’s Villages in Somaliland is part of SOS Children’s Villages International, the umbrella organization to which all SOS Children’s Villages including SOS in Somaliland Association is affiliated. SOS Children’s Village in Somaliland is a Non-Governmental Organization (NGO) that is not for profit, non-sectarian and non-partisan and which has been in existence since 1999.

SOS Children’s Village in Somaliland is committed to the welfare of children who lost parental care or at risk of losing parental care – often ensuring that children grow up in a loving family environment, and to strengthening families and communities as a preventive measure in the fight against child abandonment and social neglect, and upholds child protection policy as part of their commitment to the protection of children and youth from abuse. Uniquely, we provide long-term, family-like care for children who have lost parental care (alternative care service), and we work with vulnerable families and communities to help strengthen them and prevent family separation (family strengthening service, FS). SOS alternative care is usually organised in the form of a cluster of SOS families, where each SOS parent cares for small group of children.

SOS Children’s Villages was established in Somaliland in 1999 and it started first operations in Sahil region. Currently, SOS Children’s Villages in Somaliland implements programs ranging from child care, child protection, youth empowerment and participation, education and emergency interventions. SOS Children’s Villages in Somaliland is operational in three regions of Somaliland: Awdal, Marodijeh and Sahil, and it had a good relationship with many stakeholders, including government institutions, local authorities at national, regional and district levels, INGOs, LNGOs and local communities, as well as other CSOs who are in and out of the operational area.

## Description of project locations and context

Somaliland is one of the Least Developed Countries (LCD) in the world. Over half of the population lives below the UN poverty line and has one of the highest youth unemployment rates where two out of three young people below the age 35 years are unemployed.

Somaliland has faced consecutive droughts in the past 5 years and the cyclone that hit in mid-2018 affected severely the livelihoods of the people living in the coastal area of Sahil and Awdal regions. With this protracted draughts as well as the effects of the cyclone, pastoralist and agro-pastoralist families lost their livestock, agricultural plots and shelter, and as a result of this, moved to urban areas. In addition, children under 5 years represent more than one-quarter of all those affected and are the most at risk of malnutrition and water and sanitation hygiene (WASH) related illnesses and other childhood diseases.

SOS Children’s villages in Somaliland in partnership with Dutch relief alliance (DRA)  has been  implementing the Somali joint Response Project (SOS Children’s Village in SOMALILAND EMERGENCY PROJECT) for the last three years in Maroodi-Jeex, Sahil and Awdal Regions, targeting  most vulnerable households, focusing on the following sectors and modalities: Water, Sanitation and Hygiene (WASH), Food Security and livelihood (Agricultural and Fisheries production, Food Distribution, IGA)   Multipurpose Cash (MPC) and Protection with the objective of improving the livelihoods, sanitation, hygiene and protecting vulnerable people for the targeted households in the above locations and to ‘ contribute to children’s and youth’s rights and family preservation.

SOS Children’s Village in Somaliland, Emergency Response Project has been working in Awdal (Hamarta, Heego Lughaya, Fuguho, Hadeyta and Badanbad), Marodi-jeh (Hargeisa, Sallahley, Balli-Gubadle and Darasalam) and Sahil (Madhera, Bulo-har and Cel-shikh) regions in Somaliland.

## Rationale and overall objective of the request for proposal of the evaluation of Somali Joint Response Project.

After 3 years of implementation of Emergency Response Project (ERP), SOS Children Villages in Somaliland wants to evaluate the emergency Response Project (ERP), to assess the impact the project has made on the lives of the beneficiaries including families, children and young people, as well as their communities as a result of the project interventions.

- How relevant, effective, efficient, sustainable and participatory are the project interventions?

- What impact has the project made in the lives of the beneficiaries, participating children, their families and communities?

- What lessons can be drawn from the project that can be taken to further develop the project?

# Instruction to bidders

The bidders are welcome to submit their proposal for the evaluation of Somali Joint Response Project in Awdal. Maroadi Jeh and Sahil regions in Somaliland.  This bid is open to all national and international suppliers (independent consultants or companies) who are legally constituted and can provide the requested services. The bidder shall bear all costs of the bid; costs of a proposal cannot be included as a direct cost of the assignment. The proposal and all supplementary documents have to be submitted in English language. Financial bid needs to be stated in USD Currency.

## Process of Submission of Bids

To facilitate the submission of proposals, the submission duly stamped and signed can be done electronically in PDF format and sent hr@sos-somaliland.org Electronic submissions preferred.

The titles of submitted documents should clearly state “Technical proposal for evaluation of Somali Joint Response Project in Awdal. Marodi Jeh and Sahil regions in Somaliland. By the company/consultant title” and “Financial Proposal evaluation of Somali Joint Response Project in Awdal, Marodi Jeh and Sahil regions in Somaliland.by the company/consultant title”. Please make sure that the technical and financial proposals are handed in separately (financial proposal to be sealed in a closed envelope or a separate PDF file in case of electronic submission. During the process of evaluation, technical bids will be opened and evaluated first. The financial part of those proposals, which are shortlisted after evaluation of the technical proposal, will be opened in a second step.

## Documents to submit

- Bid submission / identification form

- Previous experience format

- Price schedule form (to be sealed in a closed envelope or a separate PDF file)

- Technical proposal

- CVs of the research team member(s) including current geographical location(s)

- Three references (at least two of them must be familiar with your work)

- An example of a recent/relevant evaluation report (if available for public use)

## Deadline for submission

The proposal has to be received by latest on 25th December 2021 by the end of the day. Proposals received after the deadline will be not be considered.

## Modification and withdrawal of bids

Proposals may be withdrawn on written request prior to the closing date of this invitation. Any corrections or changes must be received prior to the closing date. Changes must be clearly stated in comparison with the original proposal. Failure to do so will be at bidder’s own risk and disadvantage.

## Signing of the contract

SOS Children’s Villages will inform the successful bidder electronically and will send the contract form within 3 weeks after closure of the bid submission deadline. The successful bidder shall sign and date the contract, and return it to SOS Children’s in Somaliland within seven calendar days of receipt of the contract. After the contract is signed by two parties, the successful bidder shall deliver the services in accordance with the delivery schedule outlined in the bid.

## Rights of SOS Children’s Villages

- contact any or all references supplied by the bidder(s);

- request additional supporting or supplementary data (from the bidder(s));

- arrange interviews with the bidder(s);

- reject any or all proposals submitted;

- accept any proposals in whole or in part;

- negotiate with the service provider(s) who has/have attained the best rating/ranking, i.e. the one(s) providing the overall best value proposal(s);

- contract any number of candidates as required to achieve the overall evaluation objectives

## Evaluation of proposals

After the opening, each proposal will be assessed first on its technical quality and compliance and subsequently on its price. The proposal with the best overall value, composed of technical merit and price, will be considered for approval. The technical proposal is evaluated on the basis of its responsiveness to the Terms of Reference (TOR). Bidders may additionally be requested to provide additional information (virtual presentation or phone interview) to SOS Children’s Villages on the proposed services.

The criteria for selection are:

Method: The proposed method for evaluating the project is suitable

Timetable/work plan: The timetable/work plan is realistic and meet the needs of the project

Cost: The cost of the proposal is reasonable and feasible, given the other aspects of the proposal

Experience: The training and experience of the consultants in evaluations and recommendations from organisations for which the consultant(s) has previously worked

# Terms of Reference

## Objectives of the evaluation

### Overall objective

The overall objective of the final evaluation is to assess the impact of the SOS Emergency Response project has made on the lives of the beneficiaries, children, young people, their families as well as their communities as a result of the project interventions.

### Specific objectives

The Specific objectives of the SOS Emergency Response project evaluation is:

- To assess the relevance and effectiveness of the implemented activities.

- To evaluate the efficiency of the project in relation to beneficiaries, cost, and timeframe

- To assess the impact the project has made to the lives of the project beneficiaries.

- To analyse the sustainability of the ER project.

- To highlight lessons learnt, best practices and recommendations for improvements to feed back into future SOS CV programming in the same sectoral areas and using similar approaches to meeting their objectives.

At relevance and effectiveness, the evaluation should capture these areas.

- Relevance

    - To what extent do the project responds to the needs and priorities of the project beneficiaries (children, young people, families and their communities) and addressing the real needs of the target group?

    - To what extent do the families IGAs is relevant to the local market

    - To what extent do the provided seeds and tools are relevant to the needs of the farmers and fisheries

    - To that extent do the rehabilitation of water sources responded to the needs of project beneficiaries

    - To what extent do the MPC interventions supported to the vulnerable families

    - To what extent do the implemented  activities aligned with to the project documents inducing LFA, implementation plan and concept note

- Effectiveness

    - To what extent are the objectives of the project being attained (or likely to be attained?)

    - What were the effects of the project interventions (MPC, FSL, Protection and WASH) on the beneficiaries (children, young people, families and their communities) lives?

    - To what extent do the project provide skills development to the CBO beneficiaries, to prepare them to manage their IGAs?

    - To what extent do the families enable to cover basic needs of their children including Health, Education, shelter and food expenses?

    - To what extent do the family business become self-reliant?

    - To what extent do the communities understand protection concerns of their locations

    - To what extent do the project brought changes (positive/negative, intended/unintended) to the overall-wellbeing of the beneficiaries and their families?

    - Assess overall challenges faced by the internally displaced persons in the community which can prevent to the realization of their overall development?

- Participation

    - To what extent are stakeholders (beneficiaries including children and young people, partners, local authority) involved in the design, planning and implementation of the project?

    - To what extent do the project provided beneficiaries with access to relevant information regarding their involvement.

- Efficiency

    - Is the relation between input of resources and results achieved appropriate and justifiable (cost-benefit ratio)?

    - Evaluate the efficiency of the project in relation to beneficiaries, cost and timeframe of the project? What are the annual running costs and the average costs per child per month?

    - Have individual resources been used most economically? (e.g. tenders for the purchase of goods)

    - Was the project intervention implemented in timely manner?

    - Are there any alternatives for reaching the same result with less input?

    - Was the intervention implemented in the most efficient way compared to alternatives?

At impact level, the evaluation should capture these areas:

- What has happened/changed (positive and negative, intended and unintended) as a result of the project intervention?

- What difference has the project made to the beneficiaries, families and communities at large?

- Did the intervention contributed to the long-term intended results?

- Is there any specific part of the intervention which achieve a greater impact than others?

- What were the overall lessons that can be drawn from alternative care project?

Regarding sustainability, the evaluation should capture the following areas

    - To what extent do the project interventions prepared beneficiaries and their families to become resilience to the shocks (droughts and disasters?

    - To what extent is the project designed to develop the necessary local institutions (CBOs and community committees ) capacity to respond to the needs of the communities

    - To what extent did the intervention implementation consider sustainability such as capacity building of community committees and CBOs

### Scope

The evaluation will evaluate the following services in the project:

  - Food Security and Livelihoods: SOS provided food assistance to the most needy households in the target areas, provided salt production techniques training and materials to SHGs of salt production sites in Awdal coastal areas, provided fishing inputs /equipment with Volvo fishing boat to Bulo-har and Ceel-sheikh fishing cooperatives in the villages. In agriculture SOS supported farmers in Awdal and Marodi-jeh region for the provision of agriculture tools, seeds, GAP training and construction of soil bunds to reduce soil erosion.

  - Water, Sanitation and Hygiene: SOS supported the establishment and training of WASH committees in target IDP camps constructed communal latrines to improve the sanitation and hygiene situation of the IDP camps. SOS also provided hygiene and sanitation kits to the vulnerable people in the IDP camps, these kits were very important during the Covid-19 pandemic. SOS rehabilitated water sources to improve the clean water accessibility to the beneficiaries.

  - Protection: SOS has constructed child friendly space in Nasahablod C IDP Camp and strengthened protection committees and provided child rights, protection, and GBV trainings to targeted 4 IDPs. SOS conducted protection committee trainings and campaigns within target IDPs.

  - Multi-Purpose Cash: SOS supported Potentially disabled and  excluded and/or highly vulnerable community members entitled to the Unconditional Cash transfers, Strong and able-bodied men and women benefited in the Cash-for-Work activities such as agriculture, fishing and salt production activities. The main aim of the cash transfer is to improve the purchasing power parity of the vulnerable people in the target areas.

  - Localization: Working with CBO’s: The Community based organizations (CBOs) within the IDP roles is in supporting vulnerable communities within their area particularly in managing the emergency grants revolving within the beneficiaries.

## Work plan and expected deliverables

The evaluation will be carried out in 3 stages. All steps that lead to deliverables are marked in bold.

Stage 1: Prepare

Undertake all required preparations for the field evaluation: propose detailed methodology, conduct desk research, identify key informants, plan data collection process, organisation & logistics, and prepare field visit schedule. Submit and secure approval for the refined evaluation design and methodology in an inception report: document (i) proposed methodological set-up, (ii) locally adapted and proposed data collection tools. Preparation of checklists, participant lists and other management/organisational information for data collection.

Stage 2: Conduct

  - Facilitate learning during the data collection exercise.

  - Collection of data as per the agreed methodology and tools.

  - Analysis of the data.

Stage 3: Submit findings

- Preparation of a draft report in English

- Presentation of the findings to the project staff / national office staff / international team (face-to-face).

- After having received feedback from the various stakeholders – finalise the report and submit it in English [and other language if needed].

Deliverables:

  - Refinement of evaluation study design and methodology in an inception report

  - First draft of the final report in English to SOS Children’s Villages in Somaliland (face-to-face)

  - Final report

## Report criteria

The evaluation will result in the concise project evaluation report, in English with a maximum length of 35 pages including an Executive Summary. All confidential information should be kept in a separate annex to protect participants. The final report should be provided electronically and in hard copy.

The report format below must be strictly adhered to:

- Cover page

  - Title of evaluation report

  - Country, project, date of evaluation

  - Name of consultant

- Executive summary (maximum 2 pages; cross-reference pages or paragraphs in the main body)

  - Evaluated action

  - Purpose and methodology (incl. limitations and challenges)

  - Main conclusions, recommendations, and lessons learned

- Main body

  - The structure of the main body is determined by the desired results (See 2.3)

  - For each key conclusion, there should be a corresponding recommendation that is realistic, pragmatic, and operational

- Annexes

  - Terms of Reference

  - List of persons interviewed and sites visited

  - Map of areas covered by the project

## Qualification of the researcher / research team

The researcher / team of researchers must have:

        - proven competency (record of previous experiences) in project evaluations, including evaluations

        - a good understanding of development work in Somaliland

        - a good understanding of child rights and issues affecting vulnerable children and their families

        - good facilitation, organizational and interpersonal skills

        - proven experience in participatory processes and data collection methods (including age appropriate data collection methods)

        - strong analytical and conceptual skills

        - excellent written communication skills

## Logistical arrangements

When at the project location, accommodation and transport to the field will be organized by the member association, including the full coverage of costs during the entire stay of the researcher(s) (not to be included into price proposal).

National or location level staff (SOS) will be available to help organizing the interviews including contacting SOS, announcement and local preparation of evaluation, linking to community duty bearers and national authorities if required.

## Timetable

The evaluation will be conducted [insert date] and final report prepared over a period of [insert days or weeks] after the evaluation. The final report should be submitted by [insert date].

[Please fill in / customize activities and dates]

| Activities | Dates | Time frame | Location |
| --- | --- | --- | --- |
| Prepare evaluation and submit suggested data collection methods and interview partners to the contracting body (inception report) |  |  |  |
| Conduct desk research (general) |  |  |  |
| Conduct data collection (interviews etc.) |  |  |  |
| Analyses of data |  |  |  |
| Prepare draft report |  |  |  |
| Incorporate feedback and prepare final report and presentation |  |  |  |

## Duration of the contract and terms of payment

Payment will be made only upon SOS Children’s Villages acceptance of the work performed in accordance with the above described deliverables. Financial proposals should include proposed stage payments. Payment will be effected by bank transfer in the currency of billing and is due 30 days after receipt of invoice and acceptance of work.

Funding and Payment: The consultant will be paid by SOS Children’s Villages as follows:

25% on the submission and approval of inception report

25% on completion of the draft report

50% on completion of final report

Duration of contract: the contract is effective from the moment it is signed until the completion of the final report

## Notice of delay

Shall the successful bidder encounter delay in the performance of the contract which may be excusable under unavoidable circumstances; the contractor shall notify SOS Children’s Villages in writing about the causes of any such delays within one (1) week from the beginning of the delay.

After receipt of the Contractor's notice of delay, SOS Children’s Villages shall analyse the facts and extent of delay, and extend time for performance when in its judgment the facts justify such an extension.

## Copyright and other proprietary rights

SOS Children’s Villages shall be entitled to all intellectual property and other proprietary rights including, but not limited to, copyrights, and trademarks, with regard to products, processes, inventions, ideas, know-how, or documents and other materials which the Contractor has developed for SOS Children’s Villages under the Contract and which bear a direct relation to or are produced or prepared or collected in consequence of, or during the course of, the performance of the Contract. The Contractor acknowledges and agrees that such products, documents and other materials constitute works made for hire for SOS Children’s Villages.

All materials: plans, reports, estimates, recommendations, documents, and all other data compiled by or received by the Contractor under the Contract shall be the property of SOS Children’s Villages and shall be treated as confidential, and shall be delivered only to SOS Children’s Villages authorized officials on completion of work under the Contract. The external consultant is obliged to hand over all raw data collected during the evaluation to SOS Children’s Villages.

## Termination

SOS Children’s Villages reserves the right to terminate without cause this Contract at any time upon forty-five (45) days prior written notice to the Contractor, in which case SOS Children’s Villages shall reimburse the Contractor for all reasonable costs incurred by the Contractor prior to receipt of the notice of termination.

SOS Children’s Villages reserves the right to terminate the contract without any financial obligations in case if the contractor is not meeting its obligations without any prior notice:

- agreed time schedule

- withdrawal or replacement of key personal without obtaining written consent from SOS Children’s Villages

- the deliverables do not comply with requirements of ToR

# Annex

## SOS Children’s Villages child protection policy and code of conduct

SOS Children’s Villages International has a child protection policy and code of conduct that all consultants will be expected to comply with and will be required to sign a statement of commitment to the policy. This will happen upon signing of contract, together with an orientation of consultants on internal child safeguarding processes and data protection regulations.

Before the actual start of data collection, a police check is to be provided, in case any direct contact with project participants and/or any sensitive data is planned.

In addition to the above mentioned, the following key areas for ethical consideration need to be taken into account: http://childethics.com/ethical%20guidance/

Graham, A., Powell, M., Taylor, N., Anderson, D. & Fitzgerald, R. (2013). Ethical Research Involving Children. Florence: UNICEF Office of Research - Innocenti.

The successful bidder is requested to obtain written consent from all participants of the evaluation process and/or their official guardians/representatives (when applicable).

## Bid submission / identification form

This bid form must be completed, signed and returned to SOS Children’s Villages. Bids have to reflect the instructions described in the Request for Proposal and Terms of Reference.

Any requests for information regarding this Request for Proposal shall be send to [insert name and email address].

The Undersigned, having read the complete Request for Proposals including all attachments, hereby offers to supply the services specified in the schedule at the price indicated in the Price Schedule Form, in accordance with the Terms of Reference included in this document.

Offering service for: [insert organization and name].

Company/Institution Name/Individual’s Name___________________________________________

2. Address, Country: ________________________________________________________________

3. Telephone: __________________ Fax _________________ Website_______________________

4. Date of establishment (for companies): _________________________________

5. Name of Legal Representative (if applicable): _________________________________________

6. Contact Person: _____________________________________ Email: ______________________

7. Type of Company: Ltd. Other _________________________

8. Number of Staff: ______________________________________

9. Subsidiaries in the region:

Indicate name of subsidiaries and address

a)___________________________________________________________

b)___________________________________________________________

c)___________________________________________________________

Validity of Offer:	valid until:____________________________________

Date

Signature and stamp

## Previous experience form

| Description (services and products provided to the clients relevant to the current RFP) | Client | Contact person/phone, e-mail address | Date of assignment (from/to) |
| --- | --- | --- | --- |

## Price schedule form

The financial proposal needs to include all taxes.

|  | Activity | Staff involved (indicate profile) | Number of people | Number of days | Daily rate | Total price per row | % of total price |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | A | B | C | D=AxBxC | E=D/F |
| 1 | Preparation of data collection |  |  |  |  |  |  |
| 2 | Data collection |  |  |  |  |  |  |
| 4 | First draft of the final report |  |  |  |  |  |  |
| 5 | Final report |  |  |  |  |  |  |
|  | Total Price (F) |  |  |  |  |  | 100% |

Accommodation and local transportation to be covered by Member Association, not to be included into price proposal.

This proposal should be authorized, signed and stamped

________________

(Name of Organisation)

Name of representative

Address:

Telephone/Fax/Email:

## Technical proposal (guideline)

| Name of Organisation/Firm/Independent Consultant |  |
| --- | --- |
| Name of contact person for this proposal (for organisation/firm) |  |
| Address: |  |
| Phone/Fax: |  |
| E-mail: |  |

The technical bid should be concisely presented and structured in the following order to include, but not necessarily be limited to the following information listed below.

1. Quality and Relevance of Technical Proposal

- Describe all actions related to defining data collection methodology and conducting the baseline study

- Realistic work plan with time lines in accordance with ToR

- Detailed quality assurance process for data collection and analysis

2. Qualification and expertise of or organisation/team of consultants/consultant submitting proposal

- Reputation of firm/organisation and staff and individual consultant/s (competence and reliability) in carrying out evaluations

- Relevance of:

- Specialized knowledge

- Proven expertise in carrying out formative evaluations

- CVs for key staff