BUILDING CAPACITY OF SEMA IN PREPARATION FOR A NATIONWIDE NON-TECHNICAL SURVEY

INVITATION TO BID – TERM OF REFERENCE


Decades of conflict resulted in landmines and ERW contamination across Somalia severely affecting the lives and livelihoods of local populations including killing and maiming, preventing use of agricultural lands and stifling development. The Somali government signed the Anti-personal Mine Ban Convention that entered into force on 1 October 2012.  While the country has been committed to meeting its obligations, lack of funding, insecurity and thus lack of access to key areas have resulted in the country not being able to meet its targets to comply with its Anti-Personnel Mine Ban Convention (APMBC) obligations as set out in Article Five of the APMBC (as interpreted by the 2019 Oslo Action Plan (OAP). Somalia has therefore requested an extension to implement Article 5 of the convention to ´continue lifesaving humanitarian mine action activities in accessible areas and to build the capacity of state mine action institutions to take ownership of addressing the landmine contamination in the country´.
[bookmark: _GoBack]The Authority of the Somali Explosives Management Authority (SEMA) devolves from Presidential Decree 107 (6 August 2013) and is therefore recognized mine action centre for Somalia. is the recognized national focal point for the coordination of the implementation of the convention. It currently sits under and reports to the Ministry of Internal Security (MOIS) at the Federal level with several suboffices attached to local security institutions in the Federal Member States. SEMA requires capacity building to support the agency in assuming national ownership in fulfilling its obligations under the extension. For this reason, the MOIS is launching an invitation to tender to non-profit organizations with experience in explosives management and mine action, registered in Somalia, for the following contract:
Building capacity of SEMA in Preparations for a Nationwide Non-Technical Survey
· Value of Contract US$ 70,000 (5 months implementation period January – May 2022).
· The bidding entity is expected to put forward a proposal that illustrates clearly how it suggests preparing and building the institutional capacity of SEMA to be able to effectively coordinate and manage a nationwide Non-Technical Survey (NTS). 
· The bidding entity is thus expected to propose an innovative training solution/model with the appropriate resources and a methodology to conduct a pilot that prepares SEMA to conduct a nationwide NTS.
	No. 
	DESCRIPTION OF EXPECTED DELIVERABLES 

	1. 
	Inception report
An inception report should be presented at the outset that lays out the workplan and approach to the implementation of the contract. 

	1. 
	Capacity building training for SEMA on NTS with focus on the collection of socio-economic impact data
Activity:
· It is anticipated that the training will be a combination of departmental and individual training delivered for SEMA staff Including a combination of classroom-based training and on the job training and mentoring. 

	1. 
	Pilot exercise for NTS
Activity:
· It is anticipated that a pilot exercise to provide hands on monitoring will be conducted

	1. 
	Survey plan
· Support SEMA with putting together a future survey plan

	1. 
	· A Final Report 
Final report summarizes what has been delivered and anticipated impact.



· The proposal shall include:
· Bid Submission Cover Letter Form (see ITB Section 4)
· Documents Establishing the Eligibility and Qualifications of the Bidder (see ITB Section 5)
· Technical Bid (see prescribed form in ITB Section 6)
· Price Schedule (see prescribed form in ITB Section 7)
· Bid Security, if applicable (if required and as stated in the DSnos. 9-11, see prescribed Form in ITB Section 8)
· Any attachments and/or appendices to the Bid (including all those specified under the Data Sheet)

